## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-1 | Set up Java, Spring Boot, Maven, MySQL and Eclipse environment | MUST HAVE | - | all Members | 3- Completed
1 | 1 | US-2 | Design Procurement Database Schema | MUST HAVE | US-1 | Khushi | 3- Completed
1 | 1 | US-3 | Create Spring Boot Project Structure | MUST HAVE | US-1 | Goutham,Madhukar | 3- Completed
1 | 1 | US-4 | Prepare Procurement Workflow Diagram | MUST HAVE | US- | Khushi | 3- Completed
1 | 1 | US-5 | Prepare API Specification Document | MUST HAVE | US-4 | Madhukar | 3- Completed
1 | 1 | US-6 | Frequent unnecessary schema modifications | MUST HAVE | US-5 | Khushi,Goutham | 3- Completed
1 | 1 | US-7 | sql intailization form the cloned project structure | MUST HAVE | US-3 | chaithanya | 3- Completed
2 | 2 | US-8 | Design purchase requisition creation workflow | MUST HAVE | US-2 | Khushi | 3- Completed
2 | 2 | US-9 | Develop purchase requisition creation and submission module | MUST HAVE | US-8 | Goutham,Madhukar | 3- Completed
2 | 2 | US-10 | Implement configurable multi-level approval mechanism | MUST HAVE | US-9 | Khushi | 3- Completed
2 | 2 | US-11 | Configure department-wise approval hierarchy | MUST HAVE | US-10 | chaithanya | 3- Completed
2 | 2 | US-12 | Automate procurement request routing and approval processing | MUST HAVE | US-11 | Goutham | 3- Completed
2 | 2 | US-13 | Implement workflow monitoring and exception handling | SHOULD HAVE | US-12 | Madhukar | 3- Completed
2 | 2 | US-14 | Unit test procurement workflow automation engine | MUST HAVE | US-13 | Goutham,Khushi | 3- Completed
3 | 3 | US-15 | Design purchase order data model | MUST HAVE | US-2 | Khushi | 3- Completed
3 | 3 | US-16 | Develop purchase order generation from approved requisitions | MUST HAVE | US-14 | Goutham,Madhukar | 3- Completed
3 | 3 | US-17 | Implement purchase order lifecycle status tracking | MUST HAVE | US-16 | Khushi | 3- Completed
3 | 3 | US-18 | Develop fulfillment status monitoring module | MUST HAVE | US-17 | Goutham | 3- Completed
3 | 3 | US-19 | Build real-time procurement status visibility dashboard | SHOULD HAVE | US-18 | Madhukar | 3- Completed
3 | 3 | US-20 | Unit test purchase order management module | MUST HAVE | US-19 | Goutham,Khushi | 3- Completed
4 | 4 | US-21 | Develop React frontend and application navigation | MUST HAVE | US-3 | Goutham,Khushi | 3- Completed
4 | 4 | US-22 | Implement authentication and role-based access control | MUST HAVE | US-3 | Khushi | 3- Completed
4 | 4 | US-23 | Develop role-based dashboards and procurement workspace | MUST HAVE | US-22 | Goutham | 3- Completed
4 | 4 | US-24 | Implement supplier management and supplier compliance module | MUST HAVE | US-15 | Goutham | 3- Completed
4 | 4 | US-25 | Implement department, category and approval hierarchy administration | MUST HAVE | US-10 | Khushi | 3- Completed
4 | 4 | US-26 | Implement procurement reports and report export functionality | SHOULD HAVE | US-19 | Goutham | 3- Completed
4 | 4 | US-27 | Implement audit logging and administrator audit-log view | MUST HAVE | US-22 | Goutham | 3- Completed
4 | 4 | US-28 | Implement forgot-password and password-reset workflow | MUST HAVE | US-22 | Goutham,Khushi | 3- Completed
4 | 4 | US-29 | Integrate frontend modules with backend REST APIs | MUST HAVE | US-21,US-22 | Khushi | 3- Completed
4 | 4 | US-30 | Perform end-to-end testing and resolve integration defects | MUST HAVE | US-21,US-29 | Khushi,goutham | 3- Completed
4 | 4 | US-31 | Complete final UI consistency and usability improvements | SHOULD HAVE | US-21 | Khushi,Goutham | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | T-1 | Create Spring Boot Project |  |  | Goutham | Project Setup | Completed | 2
US-1 | T-2 | Add Maven Dependencies |  |  | Goutham | Configuration | Completed | 1
US-2 | T-3 | Configure MySQL Database |  |  | Khushi | database setup | Completed | 2
SPRINT 2 BACKLOG
US-8 | T-4 | Design purchase requisition creation workflow |  |  | Khushi | Design | Completed | 3
US-8 | T-5 | Prepare requisition workflow diagram |  |  | Khushi | Design | Completed | 2
US-9 | T-6 | Develop requisition creation module |  |  | Goutham | Development | Completed | 6
US-9 | T-7 | Develop requisition submission API |  |  | Madhukar | Development | Completed | 4
US-10 | T-8 | Implement multi-level approval logic |  |  | Khushi | Development | Completed | 5
US-11 | T-9 | Configure department-wise approval hierarchy |  |  | chaithanya | Configuration | Completed | 3
US-12 | T-10 | Implement automated request routing |  |  | Goutham | Development | Completed | 4
US-13 | T-11 | Implement workflow monitoring dashboard |  |  | Madhukar | Development | Completed | 5
US-13 | T-12 | Implement exception handling for workflow |  |  | Khushi | Development | Completed | 3
US-14 | T-13 | Write unit tests for workflow engine |  |  | Goutham,Khushi | Testing | Completed | 4
SPRINT 3 BACKLOG
US-15 | T-14 | Design purchase order database schema |  |  | Khushi | Design | Completed | 3
US-15 | T-15 | Prepare purchase order entity relationship diagram |  |  | Khushi | Design | Completed | 2
US-16 | T-16 | Develop purchase order generation service |  |  | Goutham | Development | Completed | 6
US-16 | T-17 | Integrate PO generation with requisition approval |  |  | Madhukar | Development | Completed | 4
US-17 | T-18 | Implement purchase order lifecycle status states |  |  | Khushi | Development | Completed | 5
US-18 | T-19 | Develop fulfillment status tracking module |  |  | Goutham | Development | Completed | 5
US-19 | T-20 | Build procurement status visibility dashboard |  |  | Goutham | Development | Completed | 6
US-20 | T-21 | Write unit tests for purchase order management |  |  | Goutham,Khushi | Testing | Completed | 4
SPRINT 4 BACKLOG
US-21 | T-22 | Develop React application layout and routing |  |  | Goutham | Frontend Development | Completed | 5
US-21 | T-23 | Implement procurement workspace and navigation |  |  | Khushi | Frontend Development | Completed | 4
US-22 | T-24 | Integrate login and registration with backend authentication APIs |  |  | Goutham | Integration | Completed | 5
US-22 | T-25 | Implement role-based route and API access |  |  | Goutham | Security | Completed | 4
US-23 | T-26 | Develop role-specific dashboards and request views |  |  | Khushi | Frontend Development | Completed | 6
US-24 | T-27 | Develop supplier management and compliance screens |  |  | Khushi | Frontend Development | Completed | 6
US-25 | T-28 | Implement department, category and approval hierarchy administration |  |  | Khushi | Configuration | Completed | 5
US-26 | T-29 | Implement procurement reports and export functionality |  |  | Goutham | Development | Completed | 6
US-27 | T-30 | Implement audit-log API and administrator audit-log page |  |  | Goutham | Development | Completed | 5
US-28 | T-31 | Implement forgot-password and reset-password flow |  |  | Khushi | Security | Completed | 5
US-29 | T-32 | Integrate frontend modules with procurement REST APIs |  |  | Khushi | Integration | Completed | 6
US-30 | T-33 | Perform end-to-end workflow testing and defect fixes |  |  | Khushi,Goutham | Testing | Completed | 8
US-31 | T-34 | Complete final UI consistency and usability improvements |  |  | Khushi | UI/UX | Completed | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | Understanding procurement requirements | Understanding procurement requirements
1 | 2 | Database design confusion | Finalized ER diagram
1 | 3 | API planning | Prepared endpoint list
1 | 4 | Workflow clarification | Updated procurement workflow
1 | 5 | Documentation review | Completed design document
2 | 1 | Clarifying requisition approval rules | Reviewed approval hierarchy requirements with mentor
2 | 2 | Designing multi-level approval logic | Finalized approval workflow design
2 | 3 | Integrating requisition module with database | Resolved schema mapping issues
2 | 4 | Testing workflow routing logic | Fixed routing configuration bug
2 | 5 | Workflow monitoring dashboard design | Completed procurement workflow engine review
3 | 1 | Understanding purchase order lifecycle requirements | Discussed PO states with mentor
3 | 2 | Designing purchase order database schema | Finalized PO entity relationships
3 | 3 | Linking PO generation with approved requisitions | Completed PO generation integration
3 | 4 | Tracking fulfillment status accurately | Implemented fulfillment status logic
3 | 5 | Dashboard performance issues | Optimized procurement status dashboard queries
4 | 1 | Frontend and backend integration issues | Validated REST API contracts and corrected integration mismatches
4 | 2 | Role-based access behavior required verification | Tested role permissions for Employee, Manager, Finance, Procurement and Admin
4 | 3 | Supplier and purchase-order workflow integration | Verified approved requests, supplier selection and purchase-order generation end to end
4 | 4 | Authentication recovery flow required testing | Tested forgot-password and single-use reset-token flow using development test accounts
4 | 5 | Final integration and UI consistency issues | Resolved final defects, verified frontend build/lint and completed final application testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint-1 | 2026-07-05 | 2026-07-09 | All members | Planning tasks before coding | Starting development without reviewing requirements | Discussing requirements with mentor | Finalized project scope and workflow diagram before implementation.
2 | Sprint-1 | 2026-07-05 | 2026-07-09 | All members | Testing database connectivity after every change | Ignoring small configuration errors | Maintaining project documentation | Successfully configured Spring Boot, Maven and MySQL environment.
3 | Sprint-2 | 2026-07-12 | 2026-07-16 | All members | Reviewing approval hierarchy before coding | Hardcoding approval levels | Daily code reviews | Implemented configurable multi-level approval workflow successfully.
4 | Sprint-2 | 2026-07-12 | 2026-07-16 | All members | Writing unit tests alongside development | Delaying integration testing | Maintaining sprint documentation | Completed procurement workflow automation engine with routing and exception handling.
5 | Sprint-3 | 2026-07-19 | 2026-07-23 | All members | Validating purchase order data model early | Skipping peer review on schema changes | Discussing blockers in daily stand-up | Implemented purchase order generation and lifecycle tracking successfully.
7 | Sprint-4 | 2026-08-08 | 2026-08-17 | All members | Integrating frontend, backend and role-based workflows early | Making UI or API changes without immediate end-to-end testing | Using daily defect tracking and validating complete procurement flows | Completed the integrated frontend and backend application with authentication, procurement workflow, supplier management, purchase orders, reports and audit logging.
8 | Sprint-4 | 2026-08-08 | 2026-08-17 | All members | Testing security, workflow and usability together before final presentation | Leaving integration defects until the end of the sprint | Maintaining clear documentation and testing with dedicated role-based accounts | Resolved final integration and authentication issues and completed the final internship presentation version.