## Defects
Sl No | Submitted By | Submitted Date | Description | Description | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Goutham | 2026-07-14 | Maven dependencies were not downloaded, causing project build failure. | Sprint 1 | Goutham | Standards | Updated pom.xml, refreshed Maven project, and executed mvn clean install. | 2026-07-14 | Closed
2 | Goutham | 2026-07-14 | Spring Boot application failed to start due to bean/dependency configuration issue. | Sprint 1 | Goutham | Logical | Identified the bean causing the error, corrected configuration, and restarted the application. | 2026-07-14 | Closed
3 | Goutham | 2026-07-14 | MySQL database connection failed because of incorrect datasource configuration. | Sprint 1 | Goutham | Logical | Corrected database URL, username, and password in application.properties and verified the connection. | 2026-07-14 | Closed
4 | Goutham | 2026-07-14 | Git merge conflict occurred while merging project files into the main branch | Sprint 1 | Madhu/Goutham | Maintainability | Resolved merge conflicts, verified code integrity, committed, and pushed the latest version. | 2026-07-14 | Closed
5 | Khushi | 2026-07-14 | Purchase Request table contained unnecessary columns, making the schema complex. | Sprint 1 | Khushi | Logical | Reviewed requirements and removed redundant attributes from the database design. | 2026-07-14 | Closed
6 | Khushi | 2026-07-14 | Workflow diagram did not correctly represent the approval flow. | Sprint 1 | Khushi | Logical | Revised the workflow to accurately show Request Submission → Manager Approval → Procurement Review → Final Status and validated it with the team. | 2026-07-14 | Closed
7 | Khushi | 2026-07-14 | Incorrect primary key and foreign key mapping in database design. | Sprint 1 | Khushi | Logical | Reviewed the database schema, identified the correct relationships, and updated the ER diagram by assigning appropriate Primary Keys and Foreign Keys. | 2026-07-14 | Closed
8 | Madhukar | 16-07-8-2026 | links mentioned in the program and response in the api call should be same | sprint 1 | Madhukar | Maintainability | Reviewed and corrected the links | 2026-07-16 | closed
9 | Madhukar | 2026-07-16 | Session Expiry Issue | sprint 1 | Madhukar | Maintainability | maintained token data in the brower | 2026-07-16 | closed
10 | Goutham | 2026-07-23 | Duplicate department names were allowed during Department creation. | Sprint 2 | Goutham | Logical | Added business validation to check unique department name before saving. | 2026-07-23 | Closed
11 | Goutham | 2026-07-23 | Active suppliers could be deleted directly from the system. | Sprint 2 | Goutham | Logical | Implemented soft delete and prevented deletion of active suppliers. | 2026-07-23 | Closed
12 | Goutham | 2026-07-23 | Bean Validation annotations were missing for mandatory supplier fields. | Sprint 2 | Goutham | Standards | Added @NotBlank, @Email, @Size, and validation messages. | 2026-07-23 | Closed
13 | Goutham | 2026-07-23 | Global Exception Handler was not returning proper HTTP status codes. | Sprint 2 | Goutham | Maintainability | Implemented centralized exception handling using @ControllerAdvice. | 2026-07-23 | Closed
14 | Goutham | 2026-07-23 | Duplicate supplier GST numbers were accepted. | Sprint 2 | Goutham | Logical | Added database unique constraint and service-layer validation. | 2026-07-23 | Closed
15 | Khushi | 2026-07-23 | Procurement Category allowed duplicate category names. | Sprint 2 | Khushi | Logical | Added uniqueness validation before insertion. | 2026-07-23 | Closed
16 | Khushi | 2026-07-23 | Approval Hierarchy permitted duplicate approval levels within the same department | Sprint 2 | Khushi | Logical | Added validation based on department and approval level combination. | 2026-07-23 | Closed
17 | Khushi | 2026-07-23 | Foreign key relationship between Category and Department was incorrectly configured. | Sprint 2 | Khushi | Logical | Updated entity mapping and corrected database relationship. | 2026-07-23 | Closed
18 | Khushi | 2026-07-23 | DTO validation was bypassed in Controller layer causing invalid requests to be processed. | Sprint 2 | Khushi | Standards | Added @Valid annotation to request DTOs. | 2026-07-23 | Closed
19 | Madhukar | 2026-07-28 | Entity Mapping Error | sprint 3 | Madhukar | Maintainability | Corrected @ManyToOne, @OneToMany, and @JoinColumn annotations. | 2026-07-28 | closed
20 | Madhukar | 2026-07-29 | Foreign Key Constraint Error | sprint 3 | Madhukar | Logical | child id ie recorded before it was being inserted before the corresponding parent record | 2026-07-29 | closed
21 | Madhukar | 2026-08-05 | JWT Authentication Integration Failure | Sprint 3 | Madhukar | User Interface | Configured Axios interceptor to attach the JWT token automatically. | 2026-08-05 | closed
22 | Madhukar | 2026-08-05 | InitializationException While Fetching Purchase Requests | Sprint 3 | Madhukar | Maintainability | Added @Transactional(readOnly = true) to all retrieval methods. | 2026-08-05 | closed
23 | Khushi | 2026-08-05 | Purchase Order Number was generated with duplicate values during concurrent requests. | Sprint 3 | Khushi | Logical | Implemented unique PO number generation using database sequence. | 2026-08-05 | Closed
24 | Khushi | 2026-08-05 | Purchase Order status was not updated after supplier confirmation. | Sprint 3 | Khushi | Maintainability | Added service logic to update PO lifecycle status automatically. | 2026-08-05 | Closed
25 | Goutham | 2026-08-05 | Purchase Order details endpoint returned incomplete supplier information. | Sprint 3 | Goutham | Maintainability | Updated entity mapping and DTO conversion to include supplier details. | 2026-08-05 | Closed
26 | Goutham | 2026-08-05 | Unauthorized users were able to access Purchase Order APIs. | Sprint 3 | Goutham | Standards | Added role-based authorization checks using Spring Security. | 2026-08-05 | Closed
27 | Khushi | 2026-08-08 | Users with insufficient roles were able to access restricted dashboard APIs. | Sprint 4 | Khushi | Standards | Added role-based authorization checks and restricted API access based on user roles. | 2026-08-08 | Closed
28 | Goutham | 2026-08-09 | REST API integration returned inconsistent error responses for invalid requests. | Sprint 4 | Goutham | Standards | Standardized API error responses using centralized exception handling and appropriate HTTP status codes. | 2026-08-09 | Closed
29 | Khushi | 2026-08-10 | Application configuration caused database/API connectivity issues during deployment. | Sprint 4 | Khushi | Standards | Corrected environment-specific configuration and database connection properties. | 2026-08-10 | Closed
30 | Chaitanya | 2026-08-09 | Manager and Finance DabasConnectivity and Login Issue | Sprint4 | Madhukar | Standards | REST API Integration returned inconsistent error responses. | 2026-08-10 | closed
31 | Khushi | 2026-08-14 | Audit logging functionality was not available for administrators to monitor procurement activities | Sprint 4 | Khushi | Logical | Implemented the Admin Audit Logs API and UI using the existing audit-log infrastructure. Added administrator-only access and newest-first audit-log retrieval. | 2026-08-15 | Closed
32 | Khushi | 2026-08-15 | Purchase order details displayed inconsistent item amount information, including incorrect overall amount/unit-price values | Sprint 4 | Khushi | Logical | Corrected purchase-order amount/item data handling and verified the PO details display with quantity, unit price, and total values | 2026-08-15 | Closed
33 | Khushi | 2026-08-15 | Forgot-password functionality was unavailable in the authentication flow. | Sprint 4 | Khushi | Logical | Implemented forgot-password and reset-password endpoints with secure single-use reset tokens and 30-minute expiration. | 2026-08-15 | Closed
34 | Khushi | 2026-08-16 | Password reset request initially returned a "No static resource api/auth/forgot-password" error during frontend testing | Sprint 4 | Khushi | Logical | Corrected the backend/frontend authentication integration and verified the forgot-password and reset-password flow using test accounts. | 2026-08-16 | Closed
35 | Khushi | 2026-08-16 | Login email and password fields had inconsistent dimensions and visual styling. | Sprint 4 | Khushi | User Interface | Standardized field width, height, border, padding, radius, background, focus state, and password visibility control styling. | 2026-08-16 | Closed
36 | Goutham | 2026-08-12 | Purchase request approval status was not consistently updated after an approval action. | Sprint 4 | Goutham | Logical | Updated the backend approval service to correctly persist the request status after each approval stage and verified the status transition through the workflow. | 2026-08-12 | Closed
37 | Goutham | 2026-08-13 | Purchase order total amount was not correctly calculated from the quantity and unit price of all items. | Sprint 4 | Goutham | Logical | Corrected the backend purchase-order calculation logic to calculate each item total using quantity × unit price and aggregate the values into the overall PO amount. | 2026-08-14 | Closed
38 | Goutham | 2026-08-14 | Supplier selection could be processed for a purchase request without properly validating the request status. | Sprint 4 | Goutham | Logical | Added backend validation to allow supplier selection only for purchase requests that have completed the required approval workflow. | 2026-08-14 | Closed
39 | Goutham | 2026-08-14 | Purchase request item data was not consistently validated before being persisted, allowing invalid quantity or price values. | Sprint 4 | Goutham | Standards | Added backend validation for purchase-request item quantity and price fields and verified invalid values are rejected before database persistence. | 2026-08-14 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others